## Project Plan
PROJECT PLAN — Mobile App Redesign (Q4 2025)
# | Task | Owner | Start | End | Days | Status | Notes
1 | Discovery & research | Alex M. | 2025-10-06 | 2025-10-17 |  | Done | 8 user interviews + competitive scan
2 | Problem statement & success metrics | Sarah W. | 2025-10-13 | 2025-10-17 |  | Done | Aligned with Q4 OKRs
3 | Information architecture v1 | Alex M. | 2025-10-20 | 2025-10-24 |  | In Progress | 5 top-level sections
4 | Wireframes — low fidelity | Alex M. | 2025-10-27 | 2025-11-03 |  | Not Started
5 | Design review with stakeholders | Sarah W. | 2025-11-04 | 2025-11-04 |  | Not Started | 1 hour
6 | Visual design — high fidelity | Alex M. | 2025-11-05 | 2025-11-19 |  | Not Started | Includes dark mode pass
7 | Prototype + usability testing | Alex M. | 2025-11-20 | 2025-11-26 |  | Not Started | 5 participants
8 | Engineering kickoff & estimation | Daniel O. | 2025-11-27 | 2025-12-01 |  | Not Started
9 | Sprint 1 — auth + nav | Daniel O. | 2025-12-02 | 2025-12-12 |  | Not Started
10 | Sprint 2 — dashboard + settings | Daniel O. | 2025-12-15 | 2025-12-26 |  | Not Started
11 | QA + bug bash | Jane K. | 2025-12-29 | 2026-01-05 |  | Not Started
12 | Soft launch (10% rollout) | Daniel O. | 2026-01-06 | 2026-01-08 |  | Not Started
13 | Full launch + post-launch monitoring | Daniel O. | 2026-01-09 | 2026-01-16 |  | Not Started