PROJECT PROPOSAL

Solar Microgrid Deployment — Off-Grid Schools Program

1. Background

Approximately 1,200 primary schools across rural Kenya remain off the national grid, limiting access to digital learning, evening study, and basic amenities like lighting and refrigeration for school meals. This proposal outlines a phased deployment of standalone solar microgrids across 60 schools over 18 months, prioritizing schools with proven community engagement and existing ICT facilities lacking reliable power.

2. Objectives

Install 5kW solar microgrid systems in 60 off-grid primary schools.

Provide reliable daytime power for ICT classes and lighting for evening study.

Train 60 school staff in basic system maintenance and safety.

Establish a community-managed maintenance fund in each participating school.

3. Methodology

Site selection will be conducted in collaboration with the Ministry of Education and county governments, using a scoring matrix that weights enrollment numbers, distance from the nearest grid connection, and demonstrated community contributions to school infrastructure. Each site will receive a 5kW system sized to power 8 classrooms, a staff room, and a computer lab, with battery storage sized for one full day of autonomy. Local technicians will be trained during installation to ensure ongoing maintenance capacity.

4. Budget Summary (KES)

| Phase | Activities | Budget |
| --- | --- | --- |
| 1 | Site assessment, community engagement, design (12 schools) | 3,200,000 |
| 2 | Procurement + installation (12 schools) | 18,000,000 |
| 3 | Training, monitoring, evaluation | 1,800,000 |
| 4 | Replication to remaining 48 schools (Y2) | 82,000,000 |
|  | Total (Y1) | 23,000,000 |

5. Timeline

| Milestone | Target | Status |
| --- | --- | --- |
| Ministry approval | M1 | Submitted |
| Phase 1 site selection | M3 | Pending |
| Phase 2 installation kickoff | M5 | Planned |
| First 12 schools online | M9 | Planned |
| Phase 3 training complete | M12 | Planned |
| Year 2 replication | M13–18 | Planned |

6. Risk Management

Tariff/duty changes on solar imports — mitigate via bulk procurement ahead of phase 2.

Community disputes over maintenance responsibility — mitigate via signed MoUs before installation.

Vandalism/theft — mitigate via fenced battery enclosures and community watch programs.