QUARTERLY REPORT

Q3 2025 Operations & Performance Review

Prepared by: Operations Team  ·  October 6, 2025  ·  Confidential

1. Executive Summary

Q3 2025 closed with revenue of KES 142M against a target of KES 138M, a 2.9% beat. Customer acquisition grew 18% QoQ, but gross margin compressed from 31% to 28% due to increased input costs. Three of four strategic initiatives launched on schedule. Operational incidents were within target, with one P1 outage in week 9 caused by a third-party API provider.

2. Headline Metrics

| Metric | Q2 Actual | Q3 Target | Q3 Actual |
| --- | --- | --- | --- |
| Revenue (KES) | 120M | 138M | 142M |
| Gross margin | 31% | 30% | 28% |
| Active customers | 11,400 | 13,200 | 13,450 |
| Net new customers | 1,820 | 1,800 | 2,050 |
| Churn rate | 4.1% | 4.0% | 3.8% |
| NPS | 42 | 45 | 47 |

3. Strategic Initiatives

Three of four strategic initiatives launched on schedule:

Customer onboarding redesign — launched week 4; first-week churn reduced from 6.1% to 4.4%.

Self-serve billing portal — launched week 7; 22% of invoices now paid via portal.

Partner API v2 — launched week 10; 14 of 18 partners migrated.

Mobile app redesign — slipped to Q4 week 2; design reviews behind schedule.

4. Operational Highlights

The platform maintained 99.94% availability against a 99.9% SLO. One P1 incident in week 9 was caused by a third-party identity provider outage; remediation included deploying a fallback auth path. Mean time to resolution for P1/P2 incidents improved from 47 minutes to 31 minutes QoQ, reflecting the new incident command rotation.

5. Risks & Open Issues

Gross margin compression may continue into Q4 — finance is preparing a pricing review.

Two key engineering hires remain open; recruitment pipeline is healthy but slow.

Mobile app launch date is at risk; design review backlog is the bottleneck.

6. Q4 Priorities

Ship the mobile app redesign by Q4 week 6.

Close the 2 open engineering hires and onboard by Q4 week 4.

Run a pricing experiment on the SME tier; report at Q4 board review.

Reduce P1/P2 incidents by 25% via the new runbook automation initiative.