## Slide 1
Weekly Status Update
Mobile App Redesign · Week 5 of 13
✓ Done
• Discovery interviews (8)
• Competitive scan
• IA v1 draft
• Stakeholder kickoff
⏳ In Progress
• Wireframes for dashboard
• Design system v2 audit
• Onboarding flow rewrite
✗ Blocked / Risks
• Engineering capacity — need contractor
• Apple review time unknown (mitigate: submit W12)

## Slide 2
Metrics This Week
8
interviews done
14
wireframes drafted
3/5
milestones on track

## Slide 3
Next Week
1. Finish wireframes for dashboard + settings (by Wed)
2. Begin visual design for onboarding (Thu-Fri)
3. 1-hour design review with VP Product (Fri 2pm)
4. Submit contractor SOW for sign-off